## Slide 1
DATE
TEAM
AREA
PROJECT
PROJECT APPROACH
TITLE
Customer Experience Enhancement
Summary of key findings from initial interviews
CX benchmarking report
Current state (As-Is) of customer journey maps
Detailed report on current state analysis
Future state (To-Be) of customer journey maps
List of recommended Initiatives
Implementation roadmap
Deliverables
Phases
Awareness and Learning
I
As-Is CX Journey Mapping
II
Current State Analysis
III
To-Be CX Journey Mapping
IV
Collect organizational data related to customers and customer journeys
Conduct initial interviews with the internal stakeholders and sample customers
Benchmark customer journey and experience against three leading entities in the same domain
Identify key insights into best practices and innovative approaches used by top performers
Activities
Identify key customer journeys for detailed analysis and define current personas
Identify and evaluate all physical and digital touch-points across all channels
Map emotional highs and lows experienced by customers throughout their journey
Develop a narrative that highlights the customer experience at each touch-point
Map the entire current customer journey and experience including actions, decisions and emotions
Conduct surveys and extensive interviews to gain an in-depth understanding of customer experience
Analyze the current customer journey for each persona to understand satisfaction levels and identify challenges
Identify pain points, customer needs, and improvement opportunities
Identify key experience pillars such as personalization or empathy to guide the design of the customer experience
Develop the current state analysis report
Redesign the future state of customer journey maps
Propose innovative initiatives to enhance the customer experience for each persona
Develop a detailed roadmap for the implementation of recommended initiatives
Recommend technological and process enhancements for each channel
Define metrics to track progress in customer experience improvement

## Slide 2
DATE
TEAM
AREA
PROJECT
PROJECT APPROACH
TITLE
Business Process Management
Comprehensive data report
Meeting agendas and minutes
Stakeholder feedback report
Process maturity report
Opportunities for Improvement in processes, policies, and procedures
Required capabilities and resources
Future business process model
Process flowcharts
Manuals for business polices and procedures
Process governance system
Training plan
Training materials and sessions
Deliverables
Phases
Diagnostic Review
I
Analysis and Visioning
II
Solution Design
III
Hand-over
IV
Collect and review organizational data
Conduct meetings with internal department heads and managers
Review strategy, business architecture and available systems
Review current services offering
Activities
Analyze and determine the current process maturity level
Analyze current policies and procedures in comparison to best practices
Identify key gaps in current processes, polices and procedures
Propose improvement opportunities to improve the maturity level of the current processes, policies, and procedures
Identify the capabilities and resources required to implement the new core and support processes
Develop / update the business process model based on best practices
Document the future business processes (To-Be) in Microsoft Visio
Develop the templates for documenting policies and procedures
Document the new business policies and procedures
Design a process governance system with a RACI matrix showing the difference responsibilities for creating, amending, cancelling and approving processes
Develop and share a training plan
Design and develop training materials
Provide training sessions to relevant stakeholders

## Slide 3
DATE
TEAM
AREA
PROJECT
PROJECT APPROACH
TITLE
Business Growth Exploration
List of emerging areas with high growth potential
Validated list of growth opportunities
Multi-criteria evaluation framework
A list of prioritized opportunities
Risk assessment report
Updated value chains
Detailed implementation roadmap
Change management workshops
Deliverables
Phases
Market Analysis
Opportunity Identification and Validation
Opportunity Evaluation and Prioritization
Growth Implementation
Conduct a comprehensive market trend analysis using data from market reports, industry publications, and government statistics
Collect and analyze competitive data
Conduct surveys and interviews with key stakeholders to enhance understanding
Identify emerging areas with high growth potential
Activities
Analyze political, economic, social, technological, legal, and environmental factors
Facilitate brainstorming sessions with cross-functional teams to identify growth opportunities based on market and PESTLE analyses
Validate and shortlist opportunities through pilot projects, market testing, or expert opinion gathering
Define criteria for evaluating growth opportunities (e.g., market size, profitability, alignment with company strategy)
Use a scoring model to screen and prioritize opportunities
Conduct risk assessments for each growth opportunity
Engage with stakeholders to align opportunities with strategic goals
Incorporate new products and services into existing value chains
Develop an implementation roadmap with timelines and milestones
Execute the growth implementation plan and implement strategies for sustained growth
Conduct change management workshops
Monitor and evaluate the implementation process continuously

## Slide 4
DATE
TEAM
AREA
PROJECT
PROJECT APPROACH
TITLE
Integrated Solution Development
Summary of preliminary data and findings
Defined scope and objectives
Timeline and milestones
Initial version of the solution
Feedback and insights gathered
Analysis of prototype performance
Updated constraints and risk analysis
Documentation of changes and improvements
Full implementation plan
Evaluation of implementation process
Documentation of lessons learned
Deliverables
Phases
Plan
Do
Check
Act
Activities
1. Refine and finalize the solution design and documentation
2. Roll out the final solution across the organization
3. Monitor and evaluate the implementation process
4. Address any issues or concerns that arise
5. Conduct a post-implementation review to assess success and document lessons learned
1. Test the prototype in a real-world environment
2. Analyze results and compare with expected outcomes
3. Identify constraints, risks, and areas for improvement
4. Make iterative improvements based on user feedback
5. Develop the current state analysis report
1. Design and develop a prototype of the proposed solution
2. Ensure compliance with project requirements and standards
3. Implement the prototype in a controlled environment
4. Facilitate workshops to gather feedback and insights
5. Collect data on performance and usability
1. Perform initial research and data gathering
2. Define project scope and objectives
3. Determine and involve key stakeholders
4. Create and approve a project plan with a timeline
5. Establish communication strategies and reporting systems