## Example
| #VALUE! | Project Charter
| Project No.:QAC001 |  |  |  | Date Charted:'7-11-2017 |  |  | Rev. No.: |  |  | Rev. Date:
Strategic Plan Scorecard (SPS)
| Problem Statement - A brief description of the problem or business case | [5 empty] | Goal Statement - Define the mission and the target of the project
| We are currently working to develop a five-year strategic plan as well as the tactical and operational plans | [5 empty] | To develop a performance measurement system that will monitor the progress of the colleges and departments and allows for report generation and comparative analysis by the end of the year
| Project Leader | [5 empty] | Project Approach - e.g. Lean Six Sigma, Traditional PM, etc.
| M. D. | [5 empty] | Plan - Design - Test - Implement
| Project Team | [5 empty] | Support Personnel - e.g. project sponsor, finance advisor, process owner, etc.
| Name |  |  | Role |  |  | Name |  |  | Role
1 | E. S. |  |  | Team member |  |  | S. B. |  |  | Process owner
2 | I. S. |  |  | Team member |  |  | A. M. |  |  | Sponsor
3
4
5
6
| Benefits | [5 empty] | Project scope
1 | Monitors & evaluates the performance against the strategic plan targets | [5 empty] | Includes the six strategic goals of the company
2 | Encourages everyone to be involved | [5 empty] | Includes all the departments
3 | Management can use the reports to make strategic decisions
4
5
6
| Assumptions | [5 empty] | Project success criteria
1 | The action plans should be provided by each department | [5 empty] | Deadline met
2 | Action plans should be clearly aligned with the strategic goals | [5 empty] | Management awareness
3 | The importance percentages should be also provided | [5 empty] | Using the system in review meetings to track performance
4 | The KPIs should be agreed on
5
6
| Deliverables | [5 empty] | Project metrics
1 | System worksheets and dashboards in MS Excel | [5 empty] | % project completion
2 | Guidelines for using the system | [5 empty] | % personnel trained
3 | [6 empty] | # of dashboards and comparative analysis designed
4
5
6
| Start Date | [5 empty] | Estimate Completion Date
| 19-Nov-2017 | [5 empty] | 19-Jan-2017
|  | Project Milestones | 1 |  | 2 |  | 3 |  | 4 |  | 5
| Description: |  | Receive action plans |  | Plan the system |  | Design reports/charts |  | Customize |  | Present
| Date: |  | 30-Nov-2017 |  | 10-Dec-2017 |  | 17-Dec-2017 |  | 31-Dec-2017 |  | 19-Jan-2018
Signatures - The signatures of the people below document approval of the formal Project Charter
[6 empty] | Signature |  |  |  |  | Date
| Project Leader: |  |  |  |  | M. D.
| Project Sponsor / Champion: |  |  |  |  | A. M.
| Process Owner: |  |  |  |  | S. B.
Financial Advisor:
All things reserved to GCPL
Guide:
Enter the elements of the project charter: project title, problem statement, goal statement, scope, project milestones, etc.
Get the digital signatures of the key stakeholders or print out a copy of the project charter and get physical signatures from them.
Once signed, the Project Leader is authorized to formally implement the project and use the necessary resources and fund to complete the project.
You need only to fill the white and blue cells.