## Identification
#VALUE! |  | Improvement Projects Identification | [6 empty] | Year: | 2018
|  |  | Unit / Department | Customer | Champion | BB, GB, PM | CI | Estimated | Summary
| # | Project Title | Area | Process Owner | Sponsor | Learder | Approach | Gains $ | Goal Statement
1 | 445 | Spoilage reduction (Line 4) | Production | Demir | Nader | Adam | Six Sigma | 320000 | Reduce spoilage in Line 4 to reach the target of 1.5% |  | Quality
2 | 461 | Stretch film wrapping usage reduction | Supply chain | Ali | Emir | Ziad | Quick wins | 11900 |  |  | Production
3 | 414 | Energy consumption reduction | EHS | John | Nader | Sami | Other | 32775 |  |  | Customer
4 | 557 | Packaging material usage reduction | Supply chain | Ali | Larry | Harvey | Six Sigma | 205000 |  |  | EHS
5 | 213 | Coolant usage reduction | Production | Demir | Larry | Steve | Six Sigma | 112200 |  |  | Supply chain
6 | 432 | 5S implementation in workshop area | Quality | Peter | Nader | Sami | Lean | 52000 |  |  | Team force
7 | 591 | Changeover time reduction (Line 4) | Production | Demir | Emir | Adam | Lean | 274000 |  |  | Other
8 | 474 | Paper and cartridge usage reduction | EHS | Jacob | Larry | Ahmad | Kaizen | 20000 | Reduction of paper and cartridge usage by 24% |  | Six Sigma
9 | 493 | Spoilage reduction (Line 6) | Production | Demir | Nader | Sameer | Six Sigma | 144000 |  |  | Lean
10 | [10 empty] | Kaizen
11 | [10 empty] | Reengineering
12 | [10 empty] | Traditional PM
13 | [10 empty] | Quick wins
14 | [10 empty] | Other
1171875
Guide:
This worksheet is where you write the information of each project after the project selection process.
All things reserved to GCPL

## Tracking
#VALUE! |  | Improvement Projects Tracking | [5 empty] | Updated: |  |  |  |  | 2018
|  |  |  | Expected | In months | Yes/No | Manual entry | Status | Yes/No | Actual | Months | Actual so far | Actual vs estimate
| # | Project Title | Start Date | End Date | Duration | Charted? | Progress % | Phase | Closed? | Finish Date | Delayed | Gains $ | Gains VAR
1 | 445 | Spoilage reduction (Line 4) | 2018-11-03 | 2019-09-03 | 10.1333 | Yes | 35% | Measure | No |  |  |  |  | Not started
2 | 461 | Stretch film wrapping usage reduction | 2018-06-18 | 2018-10-18 | 4.0667 | Yes | 100% | Completed | Yes | 2018-12-22 | 2.1667 | 12900 | 1000 | Approved
3 | 414 | Energy consumption reduction | 2018-05-18 | 2018-10-01 | 4.5333 | Yes | 60% | Canceled | No |  |  |  |  | Define
4 | 557 | Packaging material usage reduction | 2018-07-22 | 2018-12-22 | 5.1 | Yes | 100% | Completed | No | 2018-11-22 | -1 | 6400 | -198600 | Measure
5 | 213 | Coolant usage reduction | 2019-01-20 | 2019-10-20 | 9.1 | No | 0% | Approved | No |  |  |  |  | Analyse
6 | 432 | 5S implementation in workshop area | 2019-01-18 | 2019-04-18 | 3 | Yes | 80% | Control | No |  |  |  |  | Improve
7 | 591 | Changeover time reduction (Line 4) | 2019-02-02 | 2019-06-22 | 4.6667 | No | 0% | Not started | No |  |  |  |  | Control
8 | 474 | Paper and cartridge usage reduction | 2018-11-03 | 2019-01-03 | 2.0333 | Yes | 90% | Control | No |  |  |  |  | Pending
9 | 493 | Spoilage reduction (Line 6) | 2018-11-03 | 2019-09-03 | 10.1333 | Yes | 65% | Analyse | No |  |  |  |  | Postponed
10 | [13 empty] | Canceled
11 | [13 empty] | Rejected
12 | [13 empty] | Completed
13 | [13 empty] | Yes
14 | [13 empty] | No
0%
100%
19300
Guide:
This worksheet is where you track and evalate the progress of your improvement projects. It will help in evaluating the progress of the projects while running.
You need only to fill white cells. Gray cells are automatically calculated for you.
All things reserved to GCPL

## Metrics
#VALUE! |  | Metrics | Updated: | [13 empty] | 2018
|  |  | Key metric | #,$,% | In months | [12 empty] | Manual entry
| # | Project Title | The big Y | Unit | Target | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Year to date
1 | 445 | Spoilage reduction (Line 4) | Spoilage level | % | 1.5 | 2.33 | 2.12 | 2.06 | 2.23 | 1.83 | [7 empty] | 2.06 | Not started
2 | 461 | Stretch film wrapping usage reduction | [16 empty] | Approved
3 | 414 | Energy consumption reduction | [16 empty] | Define
4 | 557 | Packaging material usage reduction | [16 empty] | Measure
5 | 213 | Coolant usage reduction | [16 empty] | Analyse
6 | 432 | 5S implementation in workshop area | [16 empty] | Improve
7 | 591 | Changeover time reduction (Line 4) | [16 empty] | Control
8 | 474 | Paper and cartridge usage reduction | [16 empty] | Pending
9 | 493 | Spoilage reduction (Line 6) | [16 empty] | Postponed
10 | [18 empty] | Canceled
11 | [18 empty] | Rejected
12 | [18 empty] | Completed
13 | [18 empty] | Yes
14 | [18 empty] | No
0%
100%
Guide:
This worksheet is where you set a metric for each project to measure the performance across time.
You need only to fill white and blue cells.
All things reserved to GCPL